## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want to submit a bug report with title, project, description and stack trace so that the platform has consistent diagnostic input. | Must Have | None | Frontend Developer | Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want the backend to validate and accept bug submissions so that malformed or unsupported input is rejected safely. | Must Have | US-01 | Backend Developer | Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want uploaded text, log, JSON and CSV files to be validated for type and size so that unsafe or invalid files are not processed. | Must Have | US-01, US-02 | Frontend/Backend Developer | Completed
Sprint 1 | Sprint 1 | US-04 | As a developer, I want a historical defect knowledge base built from Apache, Eclipse and Mozilla issues so that diagnosis can use prior defects. | Must Have | Dataset preparation | Data/AI Developer | Completed
Sprint 1 | Sprint 1 | US-05 | As a developer, I want an embedding and FAISS index for historical defects so that similar issues can be retrieved efficiently. | Must Have | US-04 | AI/ML Developer | Completed
Sprint 2 | Sprint 2 | US-06 | As a developer, I want triage to classify severity, priority and affected component so that bugs can be prioritized. | Must Have | US-02, US-05 | AI/ML Developer | Completed
Sprint 2 | Sprint 2 | US-07 | As a developer, I want stack traces and logs parsed into exception type, error message and failure point so that useful evidence is extracted. | Must Have | US-02 | Backend/AI Developer | Completed
Sprint 2 | Sprint 2 | US-08 | As a developer, I want API endpoints to return structured analysis results so that the frontend can display diagnosis consistently. | Must Have | US-06, US-07 | Backend Developer | Completed
Sprint 2 | Sprint 2 | US-09 | As a developer, I want a dashboard showing knowledge-base statistics and recent submitted analyses so that I can monitor system activity. | Should Have | US-02, US-08 | Frontend/Backend Developer | Completed
Sprint 2 | Sprint 2 | US-10 | As a developer, I want shared page navigation and persistent light/dark theme behavior so that the application has a consistent interface. | Should Have | Frontend shell | Frontend Developer | Completed
Sprint 3 | Sprint 3 | US-11 | As a developer, I want root-cause analysis to retrieve relevant historical evidence and return a hypothesis with confidence and status. | Must Have | US-05, US-07 | AI/ML Developer | Completed
Sprint 3 | Sprint 3 | US-12 | As a developer, I want duplicate detection to compare a new issue with historical defects so that repeated bugs can be recognized. | Must Have | US-05, US-08 | AI/ML Developer | Completed
Sprint 3 | Sprint 3 | US-13 | As a developer, I want remediation recommendations linked to the diagnostic evidence so that I can investigate likely fixes. | Must Have | US-11, US-12 | AI/ML Developer | Completed
Sprint 3 | Sprint 3 | US-14 | As a developer, I want root-cause, duplicate and remediation findings shown in a structured result view so that the output is understandable. | Must Have | US-11, US-12, US-13 | Frontend Developer | Completed
Sprint 3 | Sprint 3 | US-15 | As a tester, I want test cases for connection errors, timeouts, key errors and memory failures so that diagnosis behavior can be checked across scenarios. | Must Have | US-06, US-07, US-11 | QA/AI Developer | Completed
Sprint 3 | Sprint 3 | US-16 | As a developer, I want insufficient-evidence cases to be identified explicitly so that the system does not present unsupported root causes as certain. | Must Have | US-11 | AI/ML Developer | Completed
Sprint 4 | Sprint 4 | US-17 | As a project lead, I want defect pattern analytics by severity, component, exception and error theme so that recurring systemic issues can be identified. | Must Have | US-08, US-14 | Backend/Frontend Developer | Completed
Sprint 4 | Sprint 4 | US-18 | As a project lead, I want analytics to filter submitted bug records and show trends so that patterns can be explored. | Should Have | US-17 | Frontend/Backend Developer | Completed
Sprint 4 | Sprint 4 | US-19 | As an administrator, I want confirmed resolved bugs and fixes recorded in a knowledge-base growth log so that the knowledge base can improve over time. | Must Have | US-13, confirmation workflow | Backend/AI Developer | Completed
Sprint 4 | Sprint 4 | US-20 | As an administrator, I want a confirmed fix to be validated before it is added to the reusable knowledge base so that incorrect fixes do not pollute retrieval. | Must Have | US-19 | QA/AI Developer | Completed
Sprint 4 | Sprint 4 | US-21 | As a developer, I want authenticated users to have their analysis history stored against their account so that records remain associated with the correct user. | Must Have | Firebase Auth configuration | Frontend/Backend Developer | Completed
Sprint 4 | Sprint 4 | US-22 | As a tester, I want end-to-end tests for submission, diagnosis, analytics and knowledge-base growth so that the full workflow is verified. | Must Have | US-17 to US-21 | QA Engineer | Completed
Sprint 4 | Sprint 4 | US-23 | As a project lead, I want the architecture, workflows and milestone documentation kept current so that the implementation can be reviewed and maintained. | Should Have | All milestones | Project Team | Completed
Sprint 4 | Sprint 4 | US-24 | As a developer, I want clear error handling for failed API responses and persistence failures so that users receive actionable feedback. | Must Have | US-02, US-08, US-21 | Frontend/Backend Developer | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 328 | 156 | 128 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Define required bug report fields and input validation rules | 2026-09-02 | 2026-09-02 | Frontend Developer | Requirements/UI | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement bug submission form for title, project, description and stack trace | 2026-09-02 | 2026-09-03 | Frontend Developer | UI Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Implement Flask API route for receiving and validating bug submissions | 2026-09-03 | 2026-09-04 | Backend Developer | API Development | Completed | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Validate supported file extensions and 10 MB upload limit | 2026-09-03 | 2026-09-04 | Frontend/Backend Developer | Validation | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-05 | Prepare and normalize Apache, Eclipse and Mozilla historical defect records | 2026-09-04 | 2026-09-06 | Data/AI Developer | Data Preparation | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Create metadata mapping for project, issue text and defect fields | 2026-09-05 | 2026-09-06 | Data/AI Developer | Data Preparation | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-07 | Generate all-MiniLM-L6-v2 embeddings for historical defects | 2026-09-06 | 2026-09-07 | AI/ML Developer | Embedding/Indexing | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-08 | Build and verify FAISS index and metadata lookup | 2026-09-07 | 2026-09-08 | AI/ML Developer | Embedding/Indexing | Completed | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-09 | Define severity, priority and affected-component classification schema | 2026-09-09 | 2026-09-09 | AI/ML Developer | Analysis | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-10 | Implement triage output with labels and confidence score | 2026-09-09 | 2026-09-10 | AI/ML Developer | AI Development | Completed | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-11 | Parse exception type, error message and failure point from logs | 2026-09-10 | 2026-09-11 | Backend/AI Developer | Log Analysis | Completed | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-12 | Return normalized JSON for triage and log-analysis results | 2026-09-11 | 2026-09-11 | Backend Developer | API Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-13 | Implement submitted analysis count and recent-record endpoints | 2026-09-12 | 2026-09-13 | Backend Developer | Analytics API | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-14 | Connect dashboard widgets to backend analytics endpoints | 2026-09-13 | 2026-09-14 | Frontend Developer | UI Integration | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-15 | Align self-contained sidebars, responsive menu and active navigation state | 2026-09-14 | 2026-09-15 | Frontend Developer | UI Development | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-16 | Persist theme preference and synchronize dark mode across pages | 2026-09-15 | 2026-09-15 | Frontend Developer | UI Development | Completed | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-17 | Retrieve top similar historical defects as root-cause evidence | 2026-09-16 | 2026-09-17 | AI/ML Developer | RAG Development | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-18 | Generate root-cause hypothesis, confidence and evidence status | 2026-09-17 | 2026-09-18 | AI/ML Developer | Root Cause Analysis | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-19 | Implement semantic similarity matching for duplicate detection | 2026-09-18 | 2026-09-19 | AI/ML Developer | Similarity Search | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-20 | Define duplicate, possible duplicate and new/unmatched result states | 2026-09-19 | 2026-09-19 | AI/ML Developer | Analysis | In Progress | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-21 | Generate remediation steps from defect evidence and diagnostic output | 2026-09-20 | 2026-09-21 | AI/ML Developer | Remediation | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-22 | Render triage, log, root-cause, duplicate and remediation findings | 2026-09-21 | 2026-09-22 | Frontend Developer | UI Integration | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-23 | Test connection refused, timeout and missing-key scenarios | 2026-09-22 | 2026-09-23 | QA/AI Developer | Testing | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-24 | Test null pointer, segmentation fault and memory failure scenarios | 2026-09-23 | 2026-09-24 | QA/AI Developer | Testing | Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-25 | Set evidence threshold and return insufficient-evidence status when needed | 2026-09-24 | 2026-09-25 | AI/ML Developer | Reliability | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-26 | Define analytics aggregations for severity, component, exception and error message | 2026-09-26 | 2026-09-27 | Backend Developer | Analytics | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-27 | Implement backend analytics aggregation endpoints | 2026-09-27 | 2026-09-28 | Backend Developer | API Development | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-28 | Implement analytics charts, date filters and project filters | 2026-09-28 | 2026-09-29 | Frontend Developer | UI Development | In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-29 | Populate Bug ID selector from submitted records rather than manual entry | 2026-09-29 | 2026-09-30 | Frontend Developer | UI Integration | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-30 | Define schema for confirmed fix and knowledge-base growth event | 2026-09-30 | 2026-10-01 | Backend/AI Developer | Data Design | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-31 | Record confirmed resolved fixes in append-only growth log | 2026-10-01 | 2026-10-02 | Backend Developer | Persistence | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-32 | Add validation gate before a confirmed fix enters reusable knowledge | 2026-10-02 | 2026-10-03 | QA/AI Developer | Validation | Planned | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T-33 | Configure shared Firebase app, Authentication and Firestore exports | 2026-10-03 | 2026-10-04 | Frontend/Backend Developer | Firebase Integration | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T-34 | Save authenticated users analysis under users/{uid}/bugAnalyses | 2026-10-04 | 2026-10-05 | Frontend/Backend Developer | Persistence | In Progress | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-35 | Run end-to-end test from bug submission through structured findings | 2026-10-05 | 2026-10-06 | QA Engineer | Testing | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-36 | Verify analytics refresh and persistence of submitted analysis records | 2026-10-06 | 2026-10-07 | QA Engineer | Testing | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-37 | Update architecture diagram and document all four milestones | 2026-10-07 | 2026-10-08 | Project Team | Documentation | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T-38 | Handle non-JSON API errors and display meaningful submission feedback | 2026-10-08 | 2026-10-08 | Frontend Developer | Error Handling | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T-39 | Verify API health, index readiness and knowledge-base statistics | 2026-10-08 | 2026-10-09 | Backend/QA Developer | Verification | In Progress | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Required fields for bug reports needed agreement. | Documented title, project, description and stack-trace fields before UI implementation.
Sprint 1 | Day 2 | Upload constraints and supported formats needed to be consistent. | Aligned frontend and backend validation for text, log, JSON and CSV files and size limits.
Sprint 1 | Day 3 | Large historical datasets required normalization before indexing. | Standardized defect fields and prepared Apache, Eclipse and Mozilla source records.
Sprint 1 | Day 4 | Embedding/index build required significant processing time and disk space. | Built the FAISS index and checked vector count and metadata alignment.
Sprint 2 | Day 1 | Severity and priority labels needed a consistent definition. | Defined a shared triage schema for severity, priority and affected component.
Sprint 2 | Day 2 | Stack traces can have different formats and incomplete failure points. | Added parsing fallbacks and returned exception type, error message and failure point.
Sprint 2 | Day 3 | Dashboard totals risked becoming stale after a new analysis. | Connected widgets to submitted-analysis endpoints and introduced a session cache for KB stats.
Sprint 2 | Day 4 | Different pages had inconsistent sidebar and theme behavior. | Standardized each page sidebar, active link, mobile overlay and persistent theme handling.
Sprint 3 | Day 1 | Retrieved defects sometimes provided weak evidence for a root cause. | Kept confidence and evidence status explicit and allowed insufficient-evidence outcomes.
Sprint 3 | Day 2 | Semantic matches could be relevant without being exact duplicates. | Separated similarity results from duplicate status and used a new/unmatched state when appropriate.
Sprint 3 | Day 3 | Fix suggestions needed to be presented as recommendations rather than guaranteed fixes. | Displayed remediation steps with diagnostic context and preserved uncertainty.
Sprint 3 | Day 4 | Integration tests exposed response-format and persistence edge cases. | Added checks for valid JSON responses, API errors and submitted-record persistence.
Sprint 4 | Day 1 | Analytics distributions required consistent field normalization. | Aligned chart normalization for count/value formats and avoided re-normalizing already normalized data.
Sprint 4 | Day 2 | Knowledge-base growth must not accept unverified fixes. | Designed a confirmed-fix record and a validation gate before reuse in the knowledge base.
Sprint 4 | Day 3 | Authenticated persistence depended on correct Firebase initialization and user state. | Centralized Firebase configuration and scoped analysis records under the signed-in user UID.
Sprint 4 | Day 4 | End-to-end verification needed to cover diagnosis, analytics and persistence together. | Prepared integrated test scenarios and checked health, index readiness and record endpoints.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-09-02 | 2026-09-08 | Frontend Developer | Start confirming validation rules before UI coding. | Stop changing input fields without updating API validation. | Continue short feedback loops between frontend and backend. | Published a shared bug-submission field and validation checklist.
2 | Sprint 1 | 2026-09-02 | 2026-09-08 | Backend Developer | Start logging API failures with actionable details. | Stop assuming every request body is valid JSON. | Continue separating route logic from data processing. | Added request validation and checked API responses with sample requests.
3 | Sprint 1 | 2026-09-02 | 2026-09-08 | Data/AI Developer | Start tracking dataset provenance and schema changes. | Stop embedding inconsistent or duplicate records. | Continue measuring index size and metadata coverage. | Normalized historical defect records and verified index/vector counts.
4 | Sprint 1 | 2026-09-02 | 2026-09-08 | QA Engineer | Start writing negative test cases alongside happy paths. | Stop treating successful upload as proof of correct processing. | Continue validating file constraints and API outcomes. | Prepared invalid-format, oversized-file and missing-field test scenarios.
5 | Sprint 2 | 2026-09-09 | 2026-09-15 | AI/ML Developer | Start recording confidence and evidence status with predictions. | Stop presenting labels without supporting context. | Continue evaluating classification on varied defect examples. | Standardized triage and log-analysis output fields.
6 | Sprint 2 | 2026-09-09 | 2026-09-15 | Frontend Developer | Start testing layout consistency at mobile widths. | Stop duplicating sidebar/theme code inconsistently between pages. | Continue using common spacing, typography and active navigation patterns. | Aligned sidebar and theme behavior across the main pages.
7 | Sprint 2 | 2026-09-09 | 2026-09-15 | Backend Developer | Start checking record persistence after each successful analysis. | Stop relying on dashboard-only state for submitted counts. | Continue exposing small, testable analytics endpoints. | Verified submitted-count and submitted-record API responses.
8 | Sprint 2 | 2026-09-09 | 2026-09-15 | QA Engineer | Start checking dashboard refresh behavior after new submissions. | Stop accepting stale charts without checking their source. | Continue documenting reproducible API test steps. | Added checks for counts, recent records and knowledge-base statistics.
9 | Sprint 3 | 2026-09-16 | 2026-09-25 | AI/ML Developer | Start evaluating root-cause evidence quality, not only confidence. | Stop treating a high similarity score as proof of causality. | Continue using historical issues as contextual evidence. | Kept insufficient-evidence status available for weak retrieval cases.
10 | Sprint 3 | 2026-09-16 | 2026-09-25 | Frontend Developer | Start presenting each agent result in a predictable structure. | Stop mixing remediation advice with confirmed root causes. | Continue keeping labels and confidence visible. | Structured triage, log, root-cause, duplicate and remediation sections.
11 | Sprint 3 | 2026-09-16 | 2026-09-25 | QA Engineer | Start testing different exception types and missing evidence. | Stop relying on a single happy-path example. | Continue keeping labels and confidence visible. | Tested connection, timeout, key, null-pointer and memory-failure cases.
12 | Sprint 3 | 2026-09-16 | 2026-09-25 | Backend Developer | Start handling unexpected API response bodies explicitly. | Stop assuming error responses always contain JSON. | Continue keeping labels and confidence visible. | Improved handling guidance for empty or malformed response bodies.
13 | Sprint 4 | 2026-09-26 | 2026-10-05 | Frontend Developer | Start verifying chart inputs before rendering. | Stop normalizing already-normalized chart data twice. | Continue keeping labels and confidence visible. | Aligned distribution data shapes and populated Bug ID from submitted records.
14 | Sprint 4 | 2026-09-26 | 2026-10-05 | Backend/AI Developer | Start requiring confirmation before learning from a proposed fix. | Stop inserting unverified remediation into reusable knowledge. | Continue keeping labels and confidence visible. | Defined the confirmed-fix and knowledge-base growth workflow.
15 | Sprint 4 | 2026-09-26 | 2026-10-05 | Firebase Developer | Start waiting for authentication state before user-scoped writes. | Stop duplicating Firebase configuration across pages. | Continue keeping labels and confidence visible. | Centralized Firebase initialization and scoped analysis storage by UID.
16 | Sprint 4 | 2026-09-26 | 2026-10-05 | QA/Project Team | Start running integrated tests after changes across modules. | Stop closing a task based only on isolated unit checks. | Continue keeping labels and confidence visible. | Prepared end-to-end checks for submission, diagnosis, analytics and persistence.