## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 2026-08-25 | Bug submission form accepts a report without a title. | Sprint 1 - M1 | Frontend Developer | Functional | Added required-field validation and clear inline error messages. | 2026-08-26 | Closed | Retested with blank and valid titles; validation behaved as expected.
2 | QA Team | 2026-08-26 | Unsupported file extensions can be selected for log upload. | Sprint 1 - M1 | Frontend Developer | Validation | Restricted uploads to TXT, LOG, JSON and CSV files and added a 10 MB size check. | 2026-08-27 | Closed | Valid and invalid file types and file sizes tested.
3 | Backend Developer | 2026-08-27 | API response parsing fails when the server returns an empty response body. | Sprint 1 - M1 | Backend Developer | Integration | Added response-status checks and safe JSON parsing with a readable error fallback. | 2026-08-29 | Closed | Verified with successful JSON, empty body and server-error responses.
4 | QA Team | 2026-08-28 | Submitted bug details are not consistently persisted after analysis. | Sprint 1 - M1 | Backend Developer | Data Persistence | Corrected the submission persistence call and aligned its arguments with the save function signature. | 2026-08-30 | Closed | Confirmed successful records are appended to submitted_bugs.jsonl.
5 | QA Team | 2026-08-29 | Triage agent assigns an inconsistent component for database connection failures. | Sprint 2 - M2 | AI/ML Developer | AI/ML | Refined component mapping rules and added representative database-error examples. | 2026-09-01 | Closed | Retested database, rendering and network-related examples.
6 | QA Team | 2026-08-30 | Stack-trace parser does not extract the failure line from some Java traces. | Sprint 2 - M2 | Backend Developer | Functional | Improved stack-trace pattern matching and fallback extraction for file and line references. | 2026-09-02 | Closed | Checked traces with and without line numbers.
7 | QA Team | 2026-08-31 | Unknown exception types are displayed as blank in the findings panel. | Sprint 2 - M2 | Frontend Developer | UI | Added a safe 'Not Detected' fallback and guarded optional response fields. | 2026-09-02 | Closed | Findings remain readable when fields are missing.
8 | QA Team | 2026-09-01 | Triage API error is not displayed clearly when backend is unavailable. | Sprint 2 - M2 | Frontend Developer | Error Handling | Added network-error messaging and loading-state recovery. | 2026-09-03 | Closed | Verified by stopping the backend and submitting a test report.
9 | QA Team | 2026-09-03 | Root-cause agent returns a confident hypothesis when retrieval evidence is weak. | Sprint 3 - M3 | AI/ML Developer | AI/ML | Added an insufficient-evidence outcome and adjusted confidence handling when retrieved context is weak. | 2026-09-06 | Closed | Tested with matched and unmatched defect examples.
10 | QA Team | 2026-09-04 | Duplicate detection marks a new issue as a duplicate despite low similarity. | Sprint 3 - M3 | AI/ML Developer | AI/ML | Applied a similarity threshold and exposed a New / Unmatched result when no suitable match exists. | 2026-09-07 | Closed | Validated both high-similarity and low-similarity cases.
11 | QA Team | 2026-09-05 | Historical search results include irrelevant projects for some queries. | Sprint 3 - M3 | AI/ML Developer | Search / Retrieval | Improved result filtering and retained project metadata for review. | 2026-09-08 | Closed | Checked results from Apache, Eclipse and Mozilla examples.
12 | QA Team | 2026-09-06 | Remediation recommendation is too generic for a connection-refused error. | Sprint 3 - M3 | AI/ML Developer | Recommendation | Added evidence-aware recommendations with diagnostic steps and regression-test guidance. | 2026-09-09 | Closed | Recommendation reviewed against the sample ConnectionError report.
13 | QA Team | 2026-09-07 | Findings page breaks when root-cause details are absent. | Sprint 3 - M3 | Frontend Developer | UI | Added null-safe rendering and explicit insufficient-evidence labels. | 2026-09-09 | Closed | Verified with partial and complete analysis responses.
14 | QA Team | 2026-09-08 | Semantic similarity page displays zero for normalized chart values. | Sprint 3 - M3 | Frontend Developer | Data Mapping | Updated distribution normalization to retain label/value records through rendering. | 2026-09-10 | Closed | Confirmed chart bars render from normalized values.
15 | QA Team | 2026-09-10 | Dashboard submitted-analysis count does not update after a new analysis. | Sprint 4 - M4 | Backend Developer | Analytics | Connected the dashboard count to the submitted-records endpoint and refreshed it after submission. | 2026-09-13 | Closed | Endpoint returned the expected total during manual verification.
16 | QA Team | 2026-09-11 | Recent analyses are not consistently ordered with the newest record first. | Sprint 4 - M4 | Frontend Developer | Analytics | Sorted records by submission timestamp in descending order before displaying the recent list. | 2026-09-14 | Closed | Checked ordering with records from different timestamps.
17 | QA Team | 2026-09-12 | Knowledge-base growth action can be submitted without selecting a bug ID. | Sprint 4 - M4 | Frontend Developer | Validation | Changed the Bug ID field to a selector populated from submitted bug records and added selection validation. | 2026-09-15 | Closed | Verified the selector is populated from the submitted-records API.
18 | QA Team | 2026-09-14 | Resolved bug is not clearly separated from a bug awaiting fix confirmation. | Sprint 4 - M4 | Backend Developer | Workflow | Added a confirmed-fix field to the growth record and required confirmation before promotion. | 2026-09-17 | Open | Pending end-to-end verification of the confirmed-fix promotion workflow.
19 | QA Team | 2026-09-16 | Pattern analytics can double-count repeated records when calculating defect trends. | Sprint 4 - M4 | Backend Developer | Analytics | Reviewing the aggregation logic to ensure records are grouped by stable bug identifiers. |  | Open | Pending validation against duplicate and repeated-submission fixtures.
20 | QA Team | 2026-09-18 | Mobile navigation overlay may remain visible after changing viewport size. | Sprint 4 - M4 | Frontend Developer | Responsive UI | Added a resize-state cleanup check and verified menu close behavior on navigation. | 2026-09-20 | Closed | Retest at desktop, tablet and mobile viewport widths.
21 | QA Team | 2026-09-20 | Knowledge-base statistics may trigger an expensive reload on each dashboard visit. | Sprint 4 - M4 | Backend Developer | Performance | Added a session-level statistics cache with explicit refresh handling. | 2026-09-22 | Closed | Checked that cached totals display immediately on repeat visits.
22 | QA Team | 2026-09-21 | Firebase analysis save can fail if authentication state has not resolved before submission. | Sprint 4 - M4 | Frontend Developer | Authentication / Integration | Pending: await Firebase authentication state before attempting to save the analysis. |  | Open | Verify signed-in, signed-out and slow-auth initialization cases before closing.

## Sheet2
Logical | BugAI Project Context
User Interface | Project | BugAI – Intelligent Bug Diagnosis Platform with Fix Recommendation Assistance
Maintainability | Coverage | Milestones 1–4: submission/knowledge base, triage/log analysis, root cause/duplicate/remediation, analytics/knowledge-base growth.
Standards | Record note | Tracker entries are project-specific sample/working records. Confirm owner, date and status against actual team logs before formal submission.
Others